## Access Facilities - March 16
| Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
| 19GOT_OO1 |  | Durham Transit Work Plan |  |  |  |  | FY 2019
| Unique Request ID: [FY Project Start year] | 19 | Project Request
| [Three letter Agency] | GOT | NEW - Not in Transit Plan
| [Project Type] | OO
| [Unique Number] | 1
Project Business Case
Provide responses to EACH of the questions below. Answer the questions as fully as possible. Enter Non-Applicable (N/A) as appropriate.
| Project Name |  | Requesting Agency |  | Project Contact |  |  | TTD Estimated Operating Cost
| Paratransit Office Space Lease & Up-fit |  | GoTriangle |  | Vinson Hines, Jr. |  |  | Current Year | 72234.75
[8 empty] | Project Cost | 1321409.968
| Estimated Start Date |  | Estimated Completion |  | FY19 Request |  |  | TTD Estimated Capital Cost
| 2018-07-01 |  | 2019-06-30 |  | 392949.9 |  |  | Current Year | 320715.15
[8 empty] | Project Cost | 916329
| Project Description | [6 empty] | Total Costs | 2237738.968
The paratransit office space lease project will offer a 5-year plan to provide space capable of housing the paratransit operations, vehicles and maintenance group while giving GoTriangle time to develop a long-term operations facilities strategy, design and plan. SWG Admin Note - This is a multi-year request. Total GoTriangle Cost of Project for 5 years = $2,237,739 Total amount proposed to Tax District (Durham or Durham and Orange? Not clear) = $ 783,209. Total FY19 Request is $ 392,950
Project Profile
P.1 | Where is this project located, who will this project serve and what are the key benefits? (Ex. Improve Transit efficiency, levels of service, etc.)
| Project Location: |  | Who will this Project serve? |  |  | What are the key benefits?
| The lease location TBD & existing regional bus operations & maintenance facility (BOMF) |  | All certified ADA passengers in the Triangle regional service area. |  |  | Improve transit efficiency, effectiveness, and readiness for current and future service levels.
P.2 | Is this project Operating, Capital or Both
P.3 | Please select the appropriate project classification(s):
P.4 | Please select whether a recurring or one-time request:
Durham Transit Plan - Orange Transit Plan
DO.1 | Which fund is this project being proposed for?
DO.2 | Was this project evaluated in the Adopted Durham or Orange Transit Plans?
If no, use the space below to describe the reason for inclusion of this project in addition to projects and services included in the Durham - Orange Transit Plan or in lieu of projects and services included in the Adopted Plan?
The temporary facility and upfit project will allow GoTriangle to immediately reposition the current Bus Operations & Maintenance Facility (BOMF) space to accommodate our current growth/workflow while freeing up office and parking spaces for new growth in service and vehicle inventory: employee, support, and revenue - related to the increased demand for future services
DO.3 | Is this an expansion or existing service (if applicable)?
DO.4 | How is this project related to projected demand for future services?
Per the Adopted Durham & Orange Plans, the transit partners are expected to work together to develop a detailed implementation plan that will identify and prioritize new enhanced bus service and facilities. Detailed studies will be conducted for larger capital projects. The outcome of these studies will impact project implementation. In the meantime, existing service will continue to operate and enhanced service will begin to deploy while larger projects are studied and gradually constructed. This project will provide GoTriangle time to develop a long-term operations facilities strategy, design and plan in coordination with the transit partners while providing existing and/or enhanced service.
DO.4 | What is your plan if the request is not funded?
If the request is not funded, it will be difficult to address our current and growing operations and maintenance needs. Based on current office capacity, all divisions within the department share limited space within the BOMF and this arrangement is no longer efficient or effective for addressing our diverse operational and maintenance needs. There is not an adequate level of office, storage, or work spaces for bus, paratransit, and maintenance staff, training personnel, or employee and fleet parking.
DO.5 | List below the Key Performance Indicators (deliverables) while this project is in progress. These performance measures will be reported quarterly.
a) | AD-Contract Start |  | AD-Contract Start
b) | CD-Construction Start |  | CD-Construction Start
c) | CD-Construction Completion |  | CD-Construction Completion
Project Monitoring Details
Capital Projects
CP.1 | Capital projects: how can outcomes be measured once this project is built/implemented?
This project will enhance the customer experience by improving the work environment for the GoTriangle frontline employees - the operators, maintenance, support and supervisory staff - all who are the tasked daily with making service delivery successful. GoTriangle envisions a regional transit system based on the following principals: Accessibility, Comfort, Security, Reliability, Cleanliness, Courtesy, and Communication/Wayfinding. Our funding request is made in order to support all of these measures, including enhanced stop amenities, better access to stops, better lighting, new vehicles, more drivers, and additional signage. Taking care of the employees by following the same principals offered to customers is the first and most important step to enhancing the customer's experience.
Operating Projects
OP.1 | Operating service: how can outcomes be measured once operations are underway?
This project will enhance our employee's experience by improving the work environment for our frontline employees - the operators, maintenance, support and supervisory staff - all who are the tasked daily with making service delivery successful.
OP.2 | For bus operating projects, please provide:
|  | a) Target Start Date |  |  | N/A
|  | b) Span |  |  | N/A
|  | c) Frequency |  |  | N/A
|  | d) Assets Used |  |  | N/A
|  | e) Geographic Termini |  |  | N/A
|  | f) Major Market Destinations Served |  |  | N/A
|  | g) Revenue Hours |  |  | N/A
OP.3 | If this is an expansion project, which organization will operate this expansion and how will it improve services?
N/A
Administration Projects
A.1 | Administration: Describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function.
N/A
P.5 | List any other relevant information not addressed.
N/A
Finance Estimates
F.1 | Estimated Project Revenues:
If there are other revenues besides Durham - Orange County Tax Revenue to support this request, please enter the anticipated revenue amounts next to the appropriate funding source for each fiscal year shown below.
Revenue
| Tax District Funding |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Durham County Tax Revenue (35%) |  | 392949.9 | 74245.5 | 76101.6375 | 78004.1784 | 79954.2829 | 81953.14 | 783208.6388
| 1/2 Cent Sales Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| $7 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| $3 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5% Vehicle Rental Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Revenue
| Federal | [7 empty] | 0
| State | [7 empty] | 0
| Other - 62% Wake Co + 3% GoTriangle |  | 729764.1 | 137884.5 | 141331.6125 | 144864.9028 | 148486.5254 | 152198.6885 | 1454530.3292
| Subtotal Other |  | 729764.1 | 137884.5 | 141331.6125 | 144864.9028 | 148486.5254 | 152198.6885 | 1454530.3292
| TOTAL Funding |  | 1122714 | 212130 | 217433.25 | 222869.0812 | 228440.8083 | 234151.8285 | 2237738.968
F.2 | Historic Triangle Transit District reimbursement: Any prior reimbursement proposed on the project?
Please provide Total YTD expenditure reimbursed on the project (including anticipated reimbursement in FY18):
[Please fill this column if your project is a existing approved project from FY18 work plan.]
F.2 | Transit Operations: Estimated appropriations to support expenses.
Enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns E-H.
Cost Break Down of Project Request
| OPERATING COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Growth Factors |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
| Salary & Fringes |  |  |  | 0 | 0 | 0 | 0 | 0
| Contracts |  |  |  | 0 | 0 | 0 | 0 | 0
Bus Operations:
| Estimated Hours |  |  |  | 0 | 0 | 0 | 0
| Cost per Hour |  |  |  | 0 | 0 | 0 | 0
| Estimated Operating Cost |  | 0 | 0 | 0 | 0 | 0 | 0
| Bus Leases |  |  |  | 0 | 0 | 0 | 0
| Park & Ride Lease |  |  |  | 0 | 0 | 0 | 0
| Office Space Rent |  | 106749 | 109565 | 112304.125 | 115111.7281 | 117989.5213 | 120939.2594 | 682658.6338
| Office Space Expenses |  | 99636 | 102565 | 105129.125 | 107757.3531 | 110451.287 | 113212.5691 | 638751.3342
| Subtotal: Bus Operations |  | 206385 | 212130 | 217433.25 | 222869.0812 | 228440.8083 | 234151.8285 | 1321409.968
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| TOTAL OPERATING COSTS |  | 206385 | 212130 | 217433.25 | 222869.0812 | 228440.8083 | 234151.8285 | 1321409.968
F.3 | Transit Capital Development: Estimated appropriations to support contractual commitments and other expenses related to proposed capital projects.
Cost Break Down of Project Request
| CAPITAL COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Design & Engineering |  | 50000 | [5 empty] | 50000
| Construction - Implementation |  | 348700 | [5 empty] | 348700
| Equipment/IT/Safety & Security |  | 398108 | [5 empty] | 398108
| 15% Contingency |  | 119521 | [5 empty] | 119521
0
| Other (Describe) | [7 empty] | 0
| TOTAL CAPITAL COSTS |  | 916329 | 0 | 0 | 0 | 0 | 0 | 916329
Assumptions for Costs and Revenues Above:
F.4 | Please state any assumption(s) used to calculate the capital and operating dollars and revenues shown above.
We are requesting that 35% of the total costs for this request be covered by the Durham & Orange County Transit Fundm (14737/41883 = 35%) In FY17, GoTriangle ACCESS performed 41,883 total trips with 14,737 trips based in Durham and Orange County. 62% funded by Wake County 3% funded by GoTriangle
0.35186
GoTriangle withdrew on March 16, 2018