## RTC Modeling
| Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
| 19GOT_CO2 |  | Durham Transit Work Plan |  |  |  |  | FY 2019
| Unique Request ID: [FY Project Start year] | 19 | Project Request
| [Three letter Agency] | GOT | NEW - Not in Transit Plan
| [Project Type] | CO
| [Unique Number] | 2
Project Business Case
Provide responses to EACH of the questions below. Answer the questions as fully as possible. Enter Non-Applicable (N/A) as appropriate.
| Project Name |  | Requesting Agency |  | Project Contact |  |  | TTD Estimated Operating Cost
| Commuter Rail RTC Modeling |  | GoTriangle |  | Patrick McDonough |  |  | Current Year | 0
[8 empty] | Project Cost | 0
| Estimated Start Date |  | Estimated Completion |  | FY19 Request |  |  | TTD Estimated Capital Cost
| 2018-07-01 |  | 2019-06-30 |  | 166667 |  |  | Current Year | 500000
[8 empty] | Project Cost | 500000
Project Description
This project will be conducted in conjunction with the North Carolina Rail Road and Norfolk Southern to complete Rail Traffic Controller (RTC) modeling activities related to the Commuter Rail project in the Major Investment Study. This project will model railroad operations in the rail corridors studied in the Major Investment Study. SWG Admin Note - this is a a continuation of the MIS and related to the FFGRPD request. Unclear the need for the Durham portion is $166,667 FY19 request is being reviewed with John Tallmadge.
Project Profile
P.1 | Where is this project located, who will this project serve and what are the key benefits? (Ex. Improve Transit efficiency, levels of service, etc.)
| Project Location: |  | Who will this Project serve? |  |  | What are the key benefits?
| The Commuter Rail Project will be located along the 37 mile corridor between Garner and Durham. |  | Commuters in Garner, Raleigh, Cary, Morrisville, RTP and Durham |  |  | The key benefit of the CRT Project is travel time reliability in the corridor.
P.2 | Is this project Operating, Capital or Both
P.3 | Please select the appropriate project classification(s):
P.4 | Please select whether a recurring or one-time request:
Durham Transit Plan - Orange Transit Plan
DO.1 | Which fund is this project being proposed for?
DO.2 | Was this project evaluated in the Adopted Durham or Orange Transit Plans?
If no, use the space below to describe the reason for inclusion of this project in addition to projects and services included in the Durham - Orange Transit Plan or in lieu of projects and services included in the Adopted Plan?
N/A
DO.3 | Is this an expansion or existing service (if applicable)?
DO.4 | How is this project related to projected demand for future services?
This project is related to demand for future services as it studies the operational characteristics and opportunities in the CRT corridor.
DO.4 | What is your plan if the request is not funded?
If this study is not funded the CRT project cannot progress and may need to be delayed.
DO.5 | List below the Key Performance Indicators (deliverables) while this project is in progress. These performance measures will be reported quarterly.
a) | CO-Specify |  | CO-Specify
b) | CO-Specify |  | CO-Specify
c) | CO-Specify |  | CO-Specify
Project Monitoring Details
Capital Projects
CP.1 | Capital projects: how can outcomes be measured once this project is built/implemented?
This expected outcome of this request is to have a reliable model of potential Commuter Rail, freight and inter-city rail (Amtrak) in the CRT corridor. The measurement of this outcome will be the completion of the RTC modeling.
Operating Projects
OP.1 | Operating service: how can outcomes be measured once operations are underway?
OP.2 | For bus operating projects, please provide:
a) Target Start Date
b) Span
c) Frequency
d) Assets Used
e) Geographic Termini
f) Major Market Destinations Served
g) Revenue Hours
OP.3 | If this is an expansion project, which organization will operate this expansion and how will it improve services?
Administration Projects
A.1 | Administration: Describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function.
P.5 | List any other relevant information not addressed.
It is assumed that the cost of this project will be shared with Wake County in accordance with the overall cost share agreement which dictates that Commuter Rail related costs be split 2/3 to Wake County and 1/3 to Durham County.
Finance Estimates
F.1 | Estimated Project Revenues:
If there are other revenues besides Durham - Orange County Tax Revenue to support this request, please enter the anticipated revenue amounts next to the appropriate funding source for each fiscal year shown below.
Revenue
| Tax District Funding |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Durham County Tax Revenue |  | 166667 | [5 empty] | 166667
1/2 Cent Sales Tax
$7 Vehicle Registration fee
$3 Vehicle Registration fee
5% Vehicle Rental Tax
Other Revenue
Federal
State
| Other (Wake) |  | 333333 | [5 empty] | 333333
| Subtotal Other |  | 156250 | [5 empty] | 333333
| TOTAL Funding |  | 500000 | [5 empty] | 500000
F.2 | Historic Triangle Transit District reimbursement: Any prior reimbursement proposed on the project?
Please provide Total YTD expenditure reimbursed on the project (including anticipated reimbursement in FY18):
[Please fill this column if your project is a existing approved project from FY18 work plan.]
F.2 | Transit Operations: Estimated appropriations to support expenses.
Enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns E-H.
Cost Break Down of Project Request
| OPERATING COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Growth Factors |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
| Salary & Fringes |  |  |  | 0 | 0 | 0 | 0 | 0
| Contracts |  |  |  | 0 | 0 | 0 | 0 | 0
Bus Operations:
| Estimated Hours |  |  |  | 0 | 0 | 0 | 0
| Cost per Hour |  |  |  | 0 | 0 | 0 | 0
| Estimated Operating Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bus Leases |  |  |  | 0 | 0 | 0 | 0
| Park & Ride Lease |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Subtotal: Bus Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| TOTAL OPERATING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
F.3 | Transit Capital Development: Estimated appropriations to support contractual commitments and other expenses related to proposed capital projects.
Cost Break Down of Project Request
| CAPITAL COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Feasibility or Other Studies |  | 500000 | [5 empty] | 500000
Land - Right of Way
Design & Engineering
Construction - Implementation
Equipment
Other (Describe)
| TOTAL CAPITAL COSTS |  | 500000 | [5 empty] | 500000
Assumptions for Costs and Revenues Above:
F.4 | Please state any assumption(s) used to calculate the capital and operating dollars and revenues shown above.
It is assumed that the cost of this project will be shared with Durham County in accordance with the overall cost share agreement which dictates that Commuter Rail related costs be split 2/3 to Wake County and 1/3 to Durham County.

## FFGARPD
| Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
| 18GOT_CD13 |  | Durham Transit Work Plan |  |  |  |  | FY 2019
| Unique Request ID: [FY Project Start year] | 18 | Project Request
| [Three letter Agency] | GOT | NEW - Not in Transit Plan
| [Project Type] | CD
| [Unique Number] | 13
Project Business Case
Provide responses to EACH of the questions below. Answer the questions as fully as possible. Enter Non-Applicable (N/A) as appropriate.
| Project Name |  | Requesting Agency |  | Project Contact |  |  | TTD Estimated Operating Cost
| COMMUTER RAIL Future Fixed Guideway Alternatives Refinement and Project Development |  | GoTriangle |  | Patrick McDonough |  |  | Current Year | 0
[8 empty] | Project Cost | 0
| Estimated Start Date |  | Estimated Completion |  | FY19 Request |  |  | TTD Estimated Capital Cost
| 2018-11-01 |  | 2020-06-30 |  | 681417 |  |  | Current Year | 681417
Project Cost
Project Description
At the conclusion of the COMMUTER RAIL(CRT) Fixed Guideway Transit Corridors Major Investment Study (Project ID: TC003-A), GoTriangle, the Capital Area Metropolitan Planning Organization and City of Raleigh will assess a range of reasonable alternatives and refine the project implementation details for each corridor or project identified. These studies will determine the preferred alternatives to advance for each identified corridor, will assess the human and natural environmental impact of the alternatives, and will refine project implementation costs and design details. These studies are a Federal requirement to progress the proposed fixed guideway projects to final design and construction. Project Cost estimates are upto 2024
Project Profile
P.1 | Where is this project located, who will this project serve and what are the key benefits? (Ex. Improve Transit efficiency, levels of service, etc.)
| Project Location: |  | Who will this Project serve? |  |  | What are the key benefits?
| Links West Durham to Garner via RTP, Morrisville, Cary, NCSU, and Raleigh along the NCRR corridor |  | Commuters traveling to major employment centers at peak hours including Downtown Durham, Downtown Raleigh, Duke Hospital, NCSU and Research Triangle Park |  |  | Guaranteed rush hour travel times in a corridor that can see delays of up to 30 minutes today; connections of regional transit hubs in Durham and Raleigh to local and regional bus as well as national rail network.
P.2 | Is this project Operating, Capital or Both
P.3 | Please select the appropriate project classification(s):
P.4 | Please select whether a recurring or one-time request:
Durham Transit Plan - Orange Transit Plan
DO.1 | Which fund is this project being proposed for?
DO.2 | Was this project evaluated in the Adopted Durham or Orange Transit Plans?
If no, use the space below to describe the reason for inclusion of this project in addition to projects and services included in the Durham - Orange Transit Plan or in lieu of projects and services included in the Adopted Plan?
DO.3 | Is this an expansion or existing service (if applicable)?
DO.4 | How is this project related to projected demand for future services?
GoTriangle's DRX bus route is already one of its most heavily used, and the bus service planning team is adding frequency in the same corridor served by CRT to accommodate growing demand in this travel market.
DO.4 | What is your plan if the request is not funded?
The region does not have an alternative strategy for high-capacity, high-reliability transit linking the destinations that would be served by commuter rail. Adding such infrastructure to I-40 and NC 147 would be extremely challenging.
DO.5 | List below the Key Performance Indicators (deliverables) while this project is in progress. These performance measures will be reported quarterly.
a) | CD-Right-of-Way Acquisition |  | CD-Right-of-Way Acquisition
b) | CD-Construction Start |  | CD-Construction Start
c) | CD-Construction Completion |  | CD-Construction Completion
Project Monitoring Details
Capital Projects
CP.1 | Capital projects: how can outcomes be measured once this project is built/implemented?
The Commuter Rail project will carry several thousand riders across the region when implemented, and guarantee travel times in a fast-growing region during rush hour. Sound land use planning carried out by local municipalities may enhance the benefits of this infrastructure in the form of increased economic development and tax base.
Operating Projects
OP.1 | Operating service: how can outcomes be measured once operations are underway?
OP.2 | For bus operating projects, please provide:
a) Target Start Date
b) Span
c) Frequency
d) Assets Used
e) Geographic Termini
f) Major Market Destinations Served
g) Revenue Hours
OP.3 | If this is an expansion project, which organization will operate this expansion and how will it improve services?
Administration Projects
A.1 | Administration: Describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function.
P.5 | List any other relevant information not addressed.
Finance Estimates
F.1 | Estimated Project Revenues:
If there are other revenues besides Durham - Orange County Tax Revenue to support this request, please enter the anticipated revenue amounts next to the appropriate funding source for each fiscal year shown below.
Revenue
| Tax District Funding |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Durham County Tax Revenue |  | 681417
1/2 Cent Sales Tax
$7 Vehicle Registration fee
$3 Vehicle Registration fee
5% Vehicle Rental Tax
Other Revenue
Federal
State
Other (Describe)
Subtotal Other
| TOTAL Funding |  | 681417 | 0 | 0 | 0 | 0 | 0 | 0
F.2 | Historic Triangle Transit District reimbursement: Any prior reimbursement proposed on the project?
Please provide Total YTD expenditure reimbursed on the project (including anticipated reimbursement in FY18):
[Please fill this column if your project is a existing approved project from FY18 work plan.]
F.2 | Transit Operations: Estimated appropriations to support expenses.
Enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns E-H.
Cost Break Down of Project Request
| OPERATING COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Growth Factors |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
| Salary & Fringes |  |  |  | 0 | 0 | 0 | 0 | 0
| Contracts |  |  |  | 0 | 0 | 0 | 0 | 0
Bus Operations:
| Estimated Hours |  |  |  | 0 | 0 | 0 | 0
| Cost per Hour |  |  |  | 0 | 0 | 0 | 0
| Estimated Operating Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bus Leases |  |  |  | 0 | 0 | 0 | 0
| Park & Ride Lease |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Subtotal: Bus Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| TOTAL OPERATING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
F.3 | Transit Capital Development: Estimated appropriations to support contractual commitments and other expenses related to proposed capital projects.
Cost Break Down of Project Request
| CAPITAL COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Feasibility or Other Studies |  | 681417 | [5 empty] | 681417
| Land - Right of Way | [7 empty] | 0
| Design & Engineering | [7 empty] | 0
| Construction - Implementation | [7 empty] | 0
| Equipment | [7 empty] | 0
| Other (Describe) | [7 empty] | 0
| TOTAL CAPITAL COSTS |  | 681417 | 0 | 0 | 0 | 0 | 0 | 681417
Assumptions for Costs and Revenues Above:
F.4 | Please state any assumption(s) used to calculate the capital and operating dollars and revenues shown above.
No
Yes
Durham
Orange
Durham & Orange
Recurring
Capital Development
Operating
Capital Vehicle Acquisition
Both
Operating - Administration
Capital Other
Purchase of Service (POS)
Capital
Operating - Other
One-Time
Expansion Service
Existing Service
No
Yes