## RTC Feas Study
| Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
| 19GOT_CD1 |  | Durham Transit Work Plan |  |  |  |  | FY 2019
| Unique Request ID: [FY Project Start year] | 19 | Project Request
| [Three letter Agency] | GOT | NEW - Not in Transit Plan
| [Project Type] | CD
| [Unique Number] | 1
Project Business Case
Provide responses to EACH of the questions below. Answer the questions as fully as possible. Enter Non-Applicable (N/A) as appropriate.
| Project Name |  | Requesting Agency |  | Project Contact |  |  | TTD Estimated Operating Cost
| New RTC Facility Feasibility Study |  | GoTriangle |  | Kevin Lewis |  |  | Current Year | 0
[8 empty] | Project Cost | 0
| Estimated Start Date |  | Estimated Completion |  | FY19 Request |  |  | TTD Estimated Capital Cost
| 2018-07-01 |  | 2019-06-01 |  | 93750 |  |  | Current Year | 250000
[8 empty] | Project Cost | 187500
Project Description
A feasibility study to deterimine the best location for a new Regional Transit Center Facility, taking into consideration current and future planned routes, land use, supply, and price. The current location of the RTC (901 Slater Rd), creates routes that overlap and hinders the efficiency of our network. This project will be funded inclusively through the Wake County Transit Plan, the Durham County Transit Plan, and the Orange County Transit Plan. The estimated capital cost displayed on this request form shows the Durham/Orange Tranit Plan portion being allocated of the total $500,000 project cost (split 62.5% Wake-37.5% Durham/Orange). SWG Admin Note - this is a multi-year request. Total Project Cost is $500,000 and Total Durham portion is $166,667. FY19 request is for $93,750
Project Profile
P.1 | Where is this project located, who will this project serve and what are the key benefits? (Ex. Improve Transit efficiency, levels of service, etc.)
| Project Location: |  | Who will this Project serve? |  |  | What are the key benefits?
| TBD by study outcome |  | All transit users |  |  | Improve transit efficiency
P.2 | Is this project Operating, Capital or Both
P.3 | Please select the appropriate project classification(s):
P.4 | Please select whether a recurring or one-time request:
Durham Transit Plan - Orange Transit Plan
DO.1 | Which fund is this project being proposed for?
DO.2 | Was this project evaluated in the Adopted Durham or Orange Transit Plans?
If no, use the space below to describe the reason for inclusion of this project in addition to projects and services included in the Durham - Orange Transit Plan or in lieu of projects and services included in the Adopted Plan?
To better serve our transit users, a more centerally located RTC will allow for more efficient service and easier access.
DO.3 | Is this an expansion or existing service (if applicable)?
DO.4 | How is this project related to projected demand for future services?
Determining a new location for the RTC will create a more efficient network.
DO.4 | What is your plan if the request is not funded?
We will look for other forms of funding.
DO.5 | List below the Key Performance Indicators (deliverables) while this project is in progress. These performance measures will be reported quarterly.
a) | CD-Project Development |  | CD-Project Development
b) | CD-Project Development |  | CD-Project Development
c) | CD-Project Development |  | CD-Project Development
Project Monitoring Details
Capital Projects
CP.1 | Capital projects: how can outcomes be measured once this project is built/implemented?
While this project is simply studying available land, the ultimate results of this project will lead to the construction of a new RTC.
Operating Projects
OP.1 | Operating service: how can outcomes be measured once operations are underway?
N/A
OP.2 | For bus operating projects, please provide:
|  | a) Target Start Date |  |  | N/A
|  | b) Span |  |  | N/A
|  | c) Frequency |  |  | N/A
|  | d) Assets Used |  |  | N/A
|  | e) Geographic Termini |  |  | N/A
|  | f) Major Market Destinations Served |  |  | N/A
|  | g) Revenue Hours |  |  | N/A
OP.3 | If this is an expansion project, which organization will operate this expansion and how will it improve services?
N/A
Administration Projects
A.1 | Administration: Describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function.
N/A
P.5 | List any other relevant information not addressed.
N/A
Finance Estimates
F.1 | Estimated Project Revenues:
If there are other revenues besides Durham - Orange County Tax Revenue to support this request, please enter the anticipated revenue amounts next to the appropriate funding source for each fiscal year shown below.
Revenue
| Tax District Funding |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Durham County Tax Revenue |  | 93750 | 93750 | 0 | 0 | 0 | 0 | 187500
| 1/2 Cent Sales Tax |  |  |  | 0 | 0 | 0 | 0 | 0
| $7 Vehicle Registration fee |  |  |  | 0 | 0 | 0 | 0 | 0
| $3 Vehicle Registration fee |  |  |  | 0 | 0 | 0 | 0 | 0
| 5% Vehicle Rental Tax |  |  |  | 0 | 0 | 0 | 0 | 0
Other Revenue
| Federal | [7 empty] | 0
| State | [7 empty] | 0
| Other (Wake Co) |  | 156250 | 156250 |  |  |  |  | 312500
| Subtotal Other |  | 156250 | 156250 | 0 | 0 | 0 | 0 | 312500
| TOTAL Funding |  | 250000 | 250000 | 0 | 0 | 0 | 0 | 500000
F.2 | Historic Triangle Transit District reimbursement: Any prior reimbursement proposed on the project?
Please provide Total YTD expenditure reimbursed on the project (including anticipated reimbursement in FY18):
[Please fill this column if your project is a existing approved project from FY18 work plan.]
F.2 | Transit Operations: Estimated appropriations to support expenses.
Enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns E-H.
Cost Break Down of Project Request
| OPERATING COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Growth Factors |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
| Salary & Fringes |  |  |  | 0 | 0 | 0 | 0 | 0
| Contracts |  |  |  | 0 | 0 | 0 | 0 | 0
Bus Operations:
| Estimated Hours |  |  |  | 0 | 0 | 0 | 0
| Cost per Hour |  |  |  | 0 | 0 | 0 | 0
| Estimated Operating Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bus Leases |  |  |  | 0 | 0 | 0 | 0
| Park & Ride Lease |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Subtotal: Bus Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| TOTAL OPERATING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
F.3 | Transit Capital Development: Estimated appropriations to support contractual commitments and other expenses related to proposed capital projects.
Cost Break Down of Project Request
| CAPITAL COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Feasibility or Other Studies |  | 250000 | 250000 |  |  |  |  | 500000
| Land - Right of Way | [7 empty] | 0
| Design & Engineering | [7 empty] | 0
| Construction - Implementation | [7 empty] | 0
| Equipment | [7 empty] | 0
| Other (Describe) | [7 empty] | 0
| TOTAL CAPITAL COSTS |  | 250000 | 250000 | 0 | 0 | 0 | 0 | 500000
Assumptions for Costs and Revenues Above:
F.4 | Please state any assumption(s) used to calculate the capital and operating dollars and revenues shown above.
1. Derived from the City of Durham and the DCHC MPO. Presentation of the sheet provided by the City of Durham at the "DCHC MPO training for locally managed projects" August 31, 2016. File accessed http://www.dchcmpo.org/publications/lmpt/default.asp NCDOT_Cost Estimation Tool-Revised.xlsx. 2. Cost Projections for Park and Rides developed by computing the cost to construct a park and ride lot and averaging the construction cost over the number of spaces and the "NCDOT "Construction Per Mile" accessed from https://www.ncdot.gov/download/performance/CostEstimateGuide.xls January 2017". Bus bays and other amenities were added as separate items. The park and ride lot assumes asphalt paving, curb, lighting, sidewalk, landscaping, storm drainage, storm treatment and pavement markings. Construction costs were taken from the NCDOT Central Let Resources - '2016 Bid Averages - 6 mths.xls'" (https://connect.ncdot.gov/letting/pages/central-letting-resources.aspx). Additional cost estimating provided by RS Means Online, an estimating program used widely in the construction industry and used by Professional Engineers, Architects and Contractors. 3. Professional Services and Construction projected costs rounded up to nearest $100,000, as shown in the summary. 4. Original Worksheet Items not shown: Inflation for future years, NCDOT Reimbursements, and Transportation funding. 5. Real Estate costs assumes purchase of property versus leasing property. Ownership of property allows for the greatest flexibility for the Transit Agency. 6. Project schedule and costs can be refined as the scope is refined. Scope information provided by Regional Services 9/25/17.