## ToCH Legion
Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
19CHT_CD2 |  | Orange Transit Work Plan |  |  |  |  | FY 2019
Unique Request ID: [FY Project Start year] | 19 | Project Request
[Three letter Agency] | CHT
[Project Type] | CD
[Unique Number] | 2
Project Business Case
Provide responses to EACH of the questions below. Answer the questions as fully as possible. Enter Non-Applicable (N/A) as appropriate.
Project Name |  | Requesting Agency |  | Project Contact |  |  | TTD Estimated Operating Cost
Legion Rd Sidewalk |  | ToCH/Chapel Hill Transit |  | Bergen Watterson |  |  | Current Year | 0
|  |  |  | bwatterson@townofchapelhill.org |  |  | Project Cost | 0
Estimated Start Date |  | Estimated Completion |  | FY19 Request |  |  | TTD Estimated Capital Cost
2018-07-01 |  | 2019-06-30 |  | 169569 |  |  | Current Year | 169569
[7 empty] | Project Cost | 169569
Project Description
Town of Chapel Hill will make a sidewalk connection along the northern end Legion Rd, completing a continuous sidewalk from Scarlett Dr to Ephesus Church Rd. An existing bus stop is located along the proposed sidewalk segment, and there are additional bus stops located near the terminus of the project on each end, all served by Chapel Hill Transit (all bus stops within 1/2 mile of the proposed project). A new crosswalk with ADA curb ramps at the Memorial Cemetery entrance is included in the project scope. Total length of new sidewalk and associated crosswalk facilities is approximately 1025 ft, and the estimated contruction cost is $169,569. This Access Improvement project will improve the bus rider experience by providing new sidewalk that improves the ability for customers to access the transit system.
Project Profile
Where is this project located, who will this project serve and what are the key benefits? (Ex. Improve Transit efficiency, levels of service, etc.)
Project Location: |  | Who will this Project serve? |  |  | What are the key benefits?
Chapel Hill, Orange County |  | Chapel Hill Residents, Visitors, Employees, UNC CH Students, UNC CH Employees |  |  | Improve access to bus stops, Improve ADA accessibility, Improve rider experience
Is this project Operating, Capital or Both
Please select the appropriate project classification(s):
Please select whether a recurring or one-time request:
Durham Transit Plan - Orange Transit Plan
Which fund is this project being proposed for?
Was this project evaluated in the Adopted Durham or Orange Transit Plans?
If no, use the space below to describe the reason for inclusion of this project in addition to projects and services included in the Durham - Orange Transit Plan or in lieu of projects and services included in the Adopted Plan?
The addition of this low-cost, high-impact project would make use of unallocated funds in the Orange County Transit Plan, in order to expand the Program of Access Improvements as described in Section 4.3 of the Transit Plan.
Is this an expansion or existing service (if applicable)?
How is this project related to projected demand for future services?
What is your plan if the request is not funded?
The project is included on the Town-wide list of missing sidewalk segments, and earns a high prioritization score based on the Town's criteria. Staff anticipates this project would be programmed in the CIP at a future date, though no funds are currently identified.
List below the Key Performance Indicators (deliverables) while this project is in progress. These performance measures will be reported quarterly.
CD-Project Development
CD-Construction Start
CD-Construction Completion
Project Monitoring Details
Capital Projects
Capital projects: how can outcomes be measured once this project is built/implemented?
The Town will use a portable pedestrian counter to determine the number of pedestrians walking along Legion Rd before and after sidewalk installation.
Operating Projects
Operating service: how can outcomes be measured once operations are underway?
For bus operating projects, please provide:
a) Target Start Date
b) Span
c) Frequency
d) Assets Used
e) Geographic Termini
f) Major Market Destinations Served
g) Revenue Hours
If this is an expansion project, which organization will operate this expansion and how will it improve services?
Administration Projects
Administration: Describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function.
n/a
List any other relevant information not addressed.
The three Chapel Hill Transit bus stop pairs on this stretch of Legion Road have a total of 23 boardings and 33 alightings daily.
Finance Estimates
Estimated Project Revenues:
If there are other revenues besides Durham - Orange County Tax Revenue to support this request, please enter the anticipated revenue amounts next to the appropriate funding source for each fiscal year shown below.
Revenue
Tax District Funding |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Durham - Orange County Tax Revenue |  | 169569 | 0 | 0 | 0 | 0 | 0 | 169569
1/2 Cent Sales Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
$7 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
$3 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5% Vehicle Rental Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Revenue
Federal |  | 0 | [5 empty] | 0
State |  | 0 | [5 empty] | 0
Other Revenue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL REVENUE |  | 169569 | 0 | 0 | 0 | 0 | 0 | 169569
Historic Triangle Transit District reimbursement: Any prior reimbursement proposed on the project?
Please provide Total YTD expenditure reimbursed on the project (including anticipated reimbursement in FY18):
[Please fill this column if your project is a existing approved project from FY18 work plan.]
Transit Operations: Estimated appropriations to support expenses.
Enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns E-H.
Cost Break Down of Project Request
OPERATING COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
Salary & Fringes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts |  |  |  | 0 | 0 | 0 | 0 | 0
Bus Operations:
Estimated Hours |  |  |  | 0 | 0 | 0 | 0
Cost per Hour |  |  |  | 0 | 0 | 0 | 0
Estimated Operating Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bus Leases |  |  |  | 0 | 0 | 0 | 0
Park & Ride Lease |  |  |  | 0 | 0 | 0 | 0
Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
Subtotal: Bus Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OPERATING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transit Capital Development: Estimated appropriations to support contractual commitments and other expenses related to proposed capital projects.
Cost Break Down of Project Request
CAPITAL COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Feasibility or Other Studies | [7 empty] | 0
Land - Right of Way | [7 empty] | 0
Design & Engineering |  | 15415 | [5 empty] | 15415
Construction - Implementation |  | 154154 | [5 empty] | 154154
Equipment | [7 empty] | 0
Other (Describe) | [7 empty] | 0
TOTAL CAPITAL COSTS |  | 169569 | 0 | 0 | 0 | 0 | 0 | 169569
Assumptions for Costs and Revenues Above:
Please state any assumption(s) used to calculate the capital and operating dollars and revenues shown above.
Capital Costs estimated using the Bicycle/Ped Facility Cost Estimator - 2014. CONSTRUCTION: Assume 985 LF of sidwalk, 5' wide, at a cost of $80 per LF. Assume curb & gutter for full segment length (none existing), at a cost of $20 per LF. No right-of-way acquisition anticipated. Utility relocation unknown. Assume 15% for Construction Admin and 20% for Contingency. 3% annual inflation since 2014. DESIGN & ENGINEERING: 10% of Construction

## ToCH Dobbins
Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
19CHT_CD1 |  | Orange Transit Work Plan |  |  |  |  | FY 2019
Unique Request ID: [FY Project Start year] | 19 | Project Request
[Three letter Agency] | CHT
[Project Type] | CD
[Unique Number] | 1
Project Business Case
Provide responses to EACH of the questions below. Answer the questions as fully as possible. Enter Non-Applicable (N/A) as appropriate.
Project Name |  | Requesting Agency |  | Project Contact |  |  | TTD Estimated Operating Cost
Dobbins Dr Sidewalk Gaps |  | ToCH/Chapel Hill Transit |  | Bergen Watterson |  |  | Current Year | 0
|  |  |  | bwatterson@townofchapelhill.org |  |  | Project Cost | 0
Estimated Start Date |  | Estimated Completion |  | FY19 Request |  |  | TTD Estimated Capital Cost
2018-07-01 |  | 2019-06-30 |  | 162615 |  |  | Current Year | 162615
[7 empty] | Project Cost | 162615
Project Description
Town of Chapel Hill will fill in 3 short gaps to complete a continuous sidewalk along Dobbins Dr from E Franklin St to north of Sage Rd. Each gap is in the vicinity (within 1/2 mile) of one or more existing bus stops served by Chapel Hill Transit. A new crosswalk and curb ramp upgrade at Foxcroft Dr is also included in the project scope. Total length of new sidewalk and associated crosswalk facilities is approximately 1040 ft, and the estimated contruction cost is $162,615. This Access Improvement project will improve the bus rider experience by providing new sidewalk that improves the ability for customers to access the transit system.
Project Profile
Where is this project located, who will this project serve and what are the key benefits? (Ex. Improve Transit efficiency, levels of service, etc.)
Project Location: |  | Who will this Project serve? |  |  | What are the key benefits?
Chapel Hill, Orange County |  | Chapel Hill Residents, Visitors, Employees, UNC CH Students, UNC CH Employees |  |  | Improve access to bus stops, Improve ADA accessibility, Improve rider experience
Is this project Operating, Capital or Both
Please select the appropriate project classification(s):
Please select whether a recurring or one-time request:
Durham Transit Plan - Orange Transit Plan
Which fund is this project being proposed for?
Was this project evaluated in the Adopted Durham or Orange Transit Plans?
If no, use the space below to describe the reason for inclusion of this project in addition to projects and services included in the Durham - Orange Transit Plan or in lieu of projects and services included in the Adopted Plan?
The addition of this small-scale, high-impact project would make use of unallocated funds in the Orange County Transit Plan, in order to expand the Program of Access Improvements as described in Section 4.3 of the Transit Plan.
Is this an expansion or existing service (if applicable)?
How is this project related to projected demand for future services?
What is your plan if the request is not funded?
The project is included on the Town-wide list of missing sidewalk segments, and earns a high prioritization score based on the Town's criteria. Staff anticipates this project would be programmed in the CIP at a future date, though no funds are currently identified.
List below the Key Performance Indicators (deliverables) while this project is in progress. These performance measures will be reported quarterly.
CD-Project Development
CD-Construction Start
CD-Construction Completion
Project Monitoring Details
Capital Projects
Capital projects: how can outcomes be measured once this project is built/implemented?
The Town will use a portable pedestrian counter to determine the number of pedestrians walking along Dobbins Drive before and after sidewalk installation.
Operating Projects
Operating service: how can outcomes be measured once operations are underway?
For bus operating projects, please provide:
a) Target Start Date
b) Span
c) Frequency
d) Assets Used
e) Geographic Termini
f) Major Market Destinations Served
g) Revenue Hours
If this is an expansion project, which organization will operate this expansion and how will it improve services?
Administration Projects
Administration: Describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function.
n/a
List any other relevant information not addressed.
The six Chapel Hill Transit bus stops on this stretch of Dobbins Drive have a total of 109 boardings and 41 alightings daily.
Finance Estimates
Estimated Project Revenues:
If there are other revenues besides Durham - Orange County Tax Revenue to support this request, please enter the anticipated revenue amounts next to the appropriate funding source for each fiscal year shown below.
Revenue
Tax District Funding |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Durham - Orange County Tax Revenue |  | 162615 | 0 | 0 | 0 | 0 | 0 | 162615
1/2 Cent Sales Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
$7 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
$3 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5% Vehicle Rental Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Revenue
Federal |  | 0 | [5 empty] | 0
State |  | 0 | [5 empty] | 0
Other Revenue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL REVENUE |  | 162615 | 0 | 0 | 0 | 0 | 0 | 162615
Historic Triangle Transit District reimbursement: Any prior reimbursement proposed on the project?
Please provide Total YTD expenditure reimbursed on the project (including anticipated reimbursement in FY18):
[Please fill this column if your project is a existing approved project from FY18 work plan.]
Transit Operations: Estimated appropriations to support expenses.
Enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns E-H.
Cost Break Down of Project Request
OPERATING COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
Salary & Fringes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts |  |  |  | 0 | 0 | 0 | 0 | 0
Bus Operations:
Estimated Hours |  |  |  | 0 | 0 | 0 | 0
Cost per Hour |  |  |  | 0 | 0 | 0 | 0
Estimated Operating Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bus Leases |  |  |  | 0 | 0 | 0 | 0
Park & Ride Lease |  |  |  | 0 | 0 | 0 | 0
Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
Subtotal: Bus Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OPERATING COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transit Capital Development: Estimated appropriations to support contractual commitments and other expenses related to proposed capital projects.
Cost Break Down of Project Request
CAPITAL COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Feasibility or Other Studies | [7 empty] | 0
Land - Right of Way | [7 empty] | 0
Design & Engineering |  | 14783 | [5 empty] | 14783
Construction - Implementation |  | 147832 | [5 empty] | 147832
Equipment | [7 empty] | 0
Other (Describe) | [7 empty] | 0
TOTAL CAPITAL COSTS |  | 162615 | 0 | 0 | 0 | 0 | 0 | 162615
Assumptions for Costs and Revenues Above:
Please state any assumption(s) used to calculate the capital and operating dollars and revenues shown above.
Capital Costs estimated using the Bicycle/Ped Facility Cost Estimator - 2014. CONSTRUCTION: Assume 1012 LF of sidwalk, 5' wide, at a cost of $80 per LF. Assume curb & gutter wherever it doesn't currently exist, at a cost of $20 per LF. No right-of-way acquisition anticipated. Utility relocation unknown. Assume 15% for Construction Admin and 20% for Contingency. 3% annual inflation since 2014. DESIGN & ENGINEERING: 10% of Construction