## FY19 Project Request
| Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2017-07-01 | Do Not Delete
| 18GOT_CD8 |  | Durham - Orange Transit Work Plan |  |  |  |  | FY 2019 |  | Form Output | FY | Agency | Project Type | Number | FY 2019
| Unique Request ID: [FY Project Start year] | 18 | Project Request Form |  |  |  |  | 2018-06-30 |  |  | 16 | CHT | AD | 1 | FY 2020
| [Three letter Agency] | GOT | For Operating or Capital Projects | [7 empty] | 17 | DCI | CD | 2 | FY 2021
| [Project Type] | CD | [8 empty] | 18 | DCO | TS | 3 | FY 2022
| [Unique Number] | 8 | [8 empty] | 19 | GOT | VP | 4 | FY 2023
| Project Business Case | [9 empty] | 20 | MPO | CO | 5
| Provide responses to EACH of the questions below. Answer the questions as fully as possible. Enter Non-Applicable (N/A) as appropriate. | [9 empty] | 21 | OPT | OO | 6
[11 empty] | 22 | TOC |  | 7
| Project Name |  | Requesting Agency |  | Project Contact |  |  | TTD Estimated Operating Cost |  |  | 23 | OTH |  | 8
| Hillsborough Park-and-Ride |  | GoTriangle |  | Kevin Lewis |  |  | Current Year | 0 |  | 24 |  |  | 9
[5 empty] | klewis@gortiangle.org |  |  | Project Cost | 41525.1562 |  | 25 |  |  | 10
| Estimated Start Date |  | Estimated Completion |  | Notes |  |  | TTD Estimated Capital Cost | [5 empty] | 11
| 2017-07-01 |  | 2020-06-30 |  | (Add notes as appropriate) |  |  | Current Year | 80000 |  |  |  |  | 12
[8 empty] | Project Cost | 1270000 |  |  |  |  | 13
| Project Description |  | Enter below a summary of the project that may later be used for the FY 2019 Durham - Orange Transit Work Plan. | [10 empty] | 14
| A park and ride in Hillsborough will provide access to the GoTriangle Orange-Durham Express Route (ODX). The park and ride will have 35-50 parking spaces and a bus stop. The park and ride will be located along US 70 as defined by the Orange County 5-Year Bus Plan. | [12 empty] | 15
| Project Profile | [8 empty] | Operating | FALSE
P.1 | Where is this project located, who will this project serve and what are the key benefits? (Ex. Improve Transit efficiency, levels of service, etc.) | [8 empty] | Capital | TRUE
| Project Location? |  | Who will this Project serve? |  |  | What are the key benefits? |  |  |  | Both | FALSE
| US70 Corridor |  | GoTriangle riders in Orange County |  |  | New park-and-ride facility |  |  |  | Operating - Administration | FALSE
[10 empty] | Operating - Other | FALSE
P.2 | Is this project Operating, Capital or Both | [8 empty] | Purchase of Service (POS) | FALSE
[10 empty] | Capital Development | TRUE
P.3 | Please select the appropriate project classification(s): | [8 empty] | Capital Vehicle Acquisition | FALSE
[10 empty] | Capital Other | FALSE
P.4 | Please select whether a recurring or one-time request: | [8 empty] | Recurring | TRUE
[10 empty] | One-Time | FALSE
| Durham Transit Plan - Orange Transit Plan | [8 empty] | Durham | FALSE
[10 empty] | Orange | TRUE
[10 empty] | Durham & Orange | FALSE
DO.1 | Which fund is this project being proposed for?
[10 empty] | YES | TRUE
DO.2 | Was this project evaluated in the Adopted Durham or Orange Transit Plans? | [8 empty] | No | FALSE
If no, use the space below to describe the reason for inclusion of this project in addition to projects and services included in the Durham - Orange Transit Plan or in lieu of projects and services included in the Adopted Plan?
N/A
DO.3 | Is this an expansion or existing service (if applicable)?
[10 empty] | Expansion Service | FALSE
DO.4 | How is this project related to projected demand for future services? | [8 empty] | Existing Service | FALSE
Park-and-ride facility owned by GoTriangle, will provide more spaces at a convienet location
DO.4 | What is your plan if the request is not funded?
If the request is delayed or denied, funding will need to come from other sources.
[13 empty] | AD | AD-Hire Date
DO.5 | List below the Key Performance Indicators (deliverables) while this project is in progress. These performance measures will be reported quarterly. | [11 empty] | CD | AD-Issue of RFP
a) | CD-Project Development | [11 empty] | TS | AD-Contract Start
b) | CD-Construction Start | [11 empty] | VP | AD-Contract Completion
c) | CD-Construction Completion | [11 empty] | CO | AD-Specify
[13 empty] | OO | CD-Right-of-Way Acquisition
| Project Monitoring Details | [12 empty] | CD-Construction Start
CD-Project Development
CD-Construction Completion
| Capital Projects | [12 empty] | CD-Specify
TS-Average Daily Ridership
CP.1 | Capital projects: how can outcomes be measured once this project is built/implemented? | [12 empty] | TS-Passengers per Hour
| Beginning of service from site | [12 empty] | TS-Revenue Hours of Service Provided
TS-Specify
| Operating Projects | [12 empty] | VP-Request Quote and request Board Approval
VP-Order/Release PO for Vehicles (bus or other)
OP.1 | Operating service: how can outcomes be measured once operations are underway? | [12 empty] | VP-Receive, inspect and accept buses
| N/A | [12 empty] | VP-Specify
CO-Specify
OP.2 | For bus operating projects, please provide: | [12 empty] | OO-Specify
|  | a) Target Start Date |  |  | N/A
|  | b) Span |  |  | N/A
|  | c) Frequency |  |  | N/A
|  | d) Assets Used |  |  | N/A
|  | e) Geographic Termini |  |  | N/A
|  | f) Major Market Destinations Served |  |  | N/A
|  | g) Revenue Hours |  |  | N/A
OP.3 | If this is an expansion project, which organization will operate this expansion and how will it improve services?
N/A
Administration Projects
A.1 | Administration: Describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function.
N/A
P.5 | List any other relevant information not addressed.
N/A
Finance Estimates
F.1 | Estimated Project Revenues:
If there are other revenues besides Durham - Orange County Tax Revenue to support this request, please enter the anticipated revenue amounts next to the appropriate funding source for each fiscal year shown below.
Revenue
| Tax Revenue |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Durham - Orange County Tax Revenue |  | 80000 | 1190000 | 10000 | 10250 | 10506.25 | 10768.9062 | 1311525.1562
| 1/2 Cent Sales Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| $7 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| $3 Vehicle Registration fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5% Vehicle Rental Tax |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Revenue
| Federal | [7 empty] | 0
| State | [7 empty] | 0
| Other (N/A) | [7 empty] | 0
| Subtotal Other |  |  |  |  | 0 | 0 | 0 | 0
| TOTAL REVENUE |  | 80000 | 1190000 | 10000 | 10250 | 10506.25 | 10768.9062 | 1311525.1562
F.2 | Historic Triangle Transit District reimbursement: Any prior reimbursement proposed on the project? | [8 empty] | YES | TRUE
| Please provide Total YTD expenditure reimbursed on the project (including anticipated reimbursement in FY18): | [5 empty] | 380000 |  |  | No | FALSE
[Please fill this column if your project is a existing approved project from FY18 work plan.]
F.2 | Transit Operations: Estimated appropriations to support expenses.
Enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns E-H.
Cost Break Down of Project Request
| OPERATING COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Growth Factors |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
| Salary & Fringes |  |  |  | 0 | 0 | 0 | 0 | 0
| Contracts |  |  |  | 0 | 0 | 0 | 0 | 0
Bus Operations:
| Estimated Hours |  |  |  | 0 | 0 | 0 | 0
| Cost per Hour |  |  |  | 0 | 0 | 0 | 0
| Estimated Operating Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bus Leases |  |  |  | 0 | 0 | 0 | 0
| Park & Ride Lease |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Other -Bus (Describe) |  |  |  | 0 | 0 | 0 | 0
| Subtotal: Bus Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (O&M) |  |  |  | 10000 | 10250 | 10506.25 | 10768.9062 | 41525.1562
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| Other (Describe) |  |  |  | 0 | 0 | 0 | 0 | 0
| TOTAL OPERATING COSTS |  | 0 | 0 | 10000 | 10250 | 10506.25 | 10768.9062 | 41525.1562
F.3 | Transit Capital Development: Estimated appropriations to support contractual commitments and other expenses related to proposed capital projects.
Cost Break Down of Project Request
| CAPITAL COSTS |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
| Feasibility or Other Studies | [7 empty] | 0
| Land - Right of Way | [7 empty] | 0
| Design & Engineering |  | 80000 | 30000 |  |  |  |  | 110000
| Construction - Implementation |  |  | 1160000 |  |  |  |  | 1160000
| Equipment | [7 empty] | 0
| Other (Describe) | [7 empty] | 0
| TOTAL CAPITAL COSTS |  | 80000 | 1190000 | 0 | 0 | 0 | 0 | 1270000
Assumptions for Costs and Revenues Above:
F.4 | Please state any assumption(s) used to calculate the capital and operating dollars and revenues shown above.
1. Derived from the City of Durham and the DCHC MPO. Presentation of the sheet provided by the City of Durham at the "DCHC MPO training for locally managed projects" August 31, 2016. File accessed http://www.dchcmpo.org/publications/lmpt/default.asp NCDOT_Cost Estimation Tool-Revised.xlsx. 2. Cost Projections for Park and Rides developed by computing the cost to construct a park and ride lot and averaging the construction cost over the number of spaces and the "NCDOT "Construction Per Mile" accessed from https://www.ncdot.gov/download/performance/CostEstimateGuide.xls January 2017". Bus bays and other amenities were added as separate items. The park and ride lot assumes asphalt paving, curb, lighting, sidewalk, landscaping, storm drainage, storm treatment and pavement markings. Construction costs were taken from the NCDOT Central Let Resources - '2016 Bid Averages - 6 mths.xls'" (https://connect.ncdot.gov/letting/pages/central-letting-resources.aspx). Additional cost estimating provided by RS Means Online, an estimating program used widely in the construction industry and used by Professional Engineers, Architects and Contractors. 3. Professional Services and Construction projected costs rounded up to nearest $100,000, as shown in the summary. 4. Original Worksheet Items not shown: Inflation for future years, NCDOT Reimbursements, and Transportation funding. 5. Real Estate costs assumes purchase of property versus leasing property. Ownership of property allows for the greatest flexibility for the Transit Agency. 6. Project schedule and costs can be refined as the scope is refined. Scope information provided by Regional Services 9/25/17.
No
Yes
Durham
Orange
Durham & Orange
Recurring
Capital Development
Operating
Capital Vehicle Acquisition
Both
Operating - Administration
Capital Other
Purchase of Service (POS)
Capital
Operating - Other
One-Time
Expansion Service
Existing Service
No
Yes

## FY19 Project Reporting
Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
18GOT_CD8 |  | Durham - Orange Transit Work Plan |  |  |  |  | FY 2019 |  |  |  |  | Quarter 1 | FY 2019
Unique Request ID: [FY Project Start year] - [Three letter Agency] _ [Project Type] - [Project Number] |  | Project Review |  |  |  |  | Quarter 1 |  |  |  |  | Quarter 2 | FY 2020
[12 empty] | Quarter 3 | FY 2021
[12 empty] | Quarter 4 | FY 2022
FUND | [12 empty] | FY 2023
Project Brief
Project Name |  | Requesting Agency |  | Project Contact |  |  | Estimated Operating Cost
Hillsborough Park-and-Ride |  | GoTriangle |  | Kevin Lewis |  |  | Current Year | 0
|  |  |  | klewis@gortiangle.org |  |  | Total Project Cost | 41525.1562
Estimated Start Date |  | Estimated Completion |  | Notes |  |  | Estimated Capital Cost
2017-07-01 |  | 2020-06-30 |  | (Add notes as appropriate) |  |  | Current Year | 80000 | FALSE
[7 empty] | Total Project Cost | 1270000 | FALSE
Project Description | [8 empty] | FALSE
A park and ride in Hillsborough will provide access to the GoTriangle Orange-Durham Express Route (ODX). The park and ride will have 35-50 parking spaces and a bus stop. The park and ride will be located along US 70 as defined by the Orange County 5-Year Bus Plan. | [10 empty] | TRUE
Alignment with Durham or Orange Transit Plan? |  |  | YES | [6 empty] | Operating | FALSE
[10 empty] | Capital Development | TRUE
Project Profile | [9 empty] | Capital Vehicle Acquisition | FALSE
Project Location? |  | Who will this Project serve? |  |  | What are the key benefits? |  |  |  |  | Both | FALSE
US70 Corridor |  | GoTriangle riders in Orange County |  |  | New park-and-ride facility |  |  |  |  | Operating - Administration | FALSE
Project Progress
Progress on Key Performance Indicators during project progress. These performance measures will be reported quarterly.
| Project Target Milestones |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
a) | CD-Project Development
b) | CD-Construction Start
c) | CD-Construction Completion
Project Status
Quarter 1 |  | Quarter 2 |  | Quarter 3 |  | Quarter 4
Documents Enclosed (if any) |  | Documents Enclosed (if any) |  | Documents Enclosed (if any) |  | Documents Enclosed (if any)
Financed Estimates - Funded by Durham and Orange Transit Plans
TTD Historic Reimbursement (Including FY18) |  | 380000
FY 2019-Quarter 1 |  | EXPENDITURE
TTD Estimated Operating Costs (YTD) |  |  | 0
TTD Total Budgeted Operating Costs |  | 0
% Triangle Tax Budget Utilized |  | 0%
FY 2019-Quarter 1 |  | EXPENDITURE
TTD Estimated Capital Costs (YTD) |  |  | 80000
TTD Total Budgeted Capital Costs |  | 80000
% Triangle Tax Budget Utilized |  | 0%
Durham
Orange
Durham & Orange
Note on B10: Praveen Sridharan: Replicated from Request Form
Note on D10: GOT: Replicated from Request form

## Exhibit A
Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
18GOT_CD8 |  | Durham - Orange Transit Work Plan |  |  |  |  | FY 2019 |  |  |  |  | FY 2019
Unique Request ID: [FY Project Start year] - [Three letter Agency] - [Project Number] |  | Exhibit A |  |  |  |  | 2018-06-30 |  |  |  |  | FY 2020
FY 2021
FY 2022
FUND | [11 empty] | FY 2023
Project Brief
Project Name |  | Requesting Agency | Contracting Agency | Project Contact |  |  | Estimated Operating Cost
Hillsborough Park-and-Ride |  | GoTriangle |  | Kevin Lewis |  |  | Current Year | 0
|  |  |  | klewis@gortiangle.org |  |  | Total Project Cost | 41525.1562
Estimated Start Date |  | Estimated Completion |  | Notes |  |  | Estimated Capital Cost
2017-07-01 |  | 2020-06-30 |  | (Add notes as appropriate) |  |  | Current Year | 80000 | FALSE
[7 empty] | Total Project Cost | 1270000 | FALSE
Project Description | [8 empty] | FALSE
A park and ride in Hillsborough will provide access to the GoTriangle Orange-Durham Express Route (ODX). The park and ride will have 35-50 parking spaces and a bus stop. The park and ride will be located along US 70 as defined by the Orange County 5-Year Bus Plan. | [10 empty] | TRUE
Alignment with Durham or Orange Transit Plan? |  |  | YES | [6 empty] | Operating | FALSE
[10 empty] | Capital Development | TRUE
Project Profile | [9 empty] | Capital Vehicle Acquisition | FALSE
Project Location? |  | Who will this Project serve? |  |  | What are the key benefits? |  |  |  |  | Both | FALSE
US70 Corridor |  | GoTriangle riders in Orange County |  |  | New park-and-ride facility |  |  |  |  | Operating - Administration | FALSE
Project Monitoring
Progress on Key Performance Indicators during project progress. These performance measures will be reported quarterly.
| Project Target Milestones |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
a) | CD-Project Development
b) | CD-Construction Start
c) | CD-Construction Completion
Project Agreement Details
Durham
Orange
Durham & Orange
Note on B10: Praveen Sridharan: Replicated from Request Form
Note on D10: Praveen Sridharan: Replicated from Request form

## ProjReq Instructions
FY 2019 Durham-Orange Transit
Project Request Instructions
Project Request Forms (Operating Expansion and Capital Requests)
Agencies are greatly encouraged to take time and effort, and to coordinate internally, before submitting requests for which funds are requested from Durham-Orange Transit. Inadequate information submitted in support of projects greatly diminishes the ability of the Durham-Orange Staff Working Group to evaluate projects for which Durham-Orange Transit funds are requested. It also prevents sufficient narrative to be developed in order to tell public, agency, and other stakeholders about future Durham-Orange Transit projects for the Draft Durham-Orange Transit Work Plan to be released in January.
In order for an operating or expansion capital request to be submitted, it must be submitted on the FY 2019 Durham-Orange Transit Work Plan Project Request Form located in the Tax District Transit Request and Reporting Template.xls, a Microsoft Excel workbook. This worksheet includes much of the narrative and financial information required to support the expansion request. For your convenience, this data automatically rolls into the Project Reporting form. For that reason, please save one Tax District Transit Request and Reporting Template for each project you request. Rename the workbook with your Unique Project ID (see below) and a version and date so that changes can be tracked as the FY 2019 process moves forward and subsequent versions are created. Agencies are encouraged to coordinate requests internally and to have one point of contact for submitting requests in agency folders.
HINT: Requesting Agencies only need to complete sections highlighted GREEN. Formulas are included in cells shaded PINK. If a question or description is not applicable to your project, type in N/A.
How to Submit Requests
E-mail each Project workbook, one for each Unique Project ID #, which contains both a Project Request sheet and a Project Reporting sheet, to DOTransitProjects@gotriangle.org.
Instructions by Section
Unique Project ID
The unique project ID is expected to identify a project for the life of the project. It is crucial to take the time to create a unique project ID for submitted projects. This would enable consistent reporting through the life-cycle of the project from request to completion. For your convenience, the spreadsheet includes Drop Down menus with appropriate coding options.
Project Business Case
Complete all cells shaded GREEN.
Project Profile
Complete all cells shaded GREEN. Also, check the appropriate boxes in sections P.2, P.3 and P.4.
Transit Plans
Complete all cells shaded GREEN. Also, check the appropriate boxes in section DO.1.
The Key Performance Indicators included in section DO.4 has the option to include standard and custom KPI's. .
For your convenience, the spreadsheet includes Drop Down menus with appropriate standard recommended KPI's based on the project type in the . In case the project requires custom KPI's, please select the "Specify" option for the appropriate project type and detail the KPI in the seperate "Describe" area
Project Monitoring Details
Complete all cells shaded GREEN. The agreement requires GoTriangle to report on project progress and monitoring. The project monitoring details are split between Capital Projects, Operating Projects and Administration.
In Example 1 below, the project type is a Capital Project. After completing section CP.1, you can collapse the cells in the Project Monitoring Details section that are not relevant skipping ahead to the Administration Projects section and then complete section P.5.
Example 1
In Example 2 below, the project type is an Operating Project. After completing sections OP.1, OP.2 and OP.3, you can collapse the cells in the Project Monitoring Details section that are not relevant skipping ahead to the Administration Projects section and then complete section P.5.
Example 2
In Example 3 below, the project type is an Administration Project. After completing section A.1, you can collapse the cells in the Project Monitoring Details section that are not relevant and then complete section P.5.
Example 3
Finance Estimates
In section F.1 Estimated Project Revenues, enter the appropriation amount requested under each applicable heading (i.e., FY19, FY20, FY21, etc.) designating the amount from Durham-Orange County Tax Revenue, Federal, State and Other revenue sources. If Other Revenue sources is applicable, type in the name of the source in cell B99 over the word “Other”. It is understood that if a project is not going to begin on July 1, 2018, the FY19 appropriation amount will be prorated accordingly. If that project is expected to continue into future years, input the annualized appropriation amount.
In section F.2 Historic reimbursements: Estimated Triangle Tax District reimbursement on the project. Please estimate FY18 reimbursements for projects that were approved in FY18 work plan. Please fill this column if your project is a existing operation or approved project from FY18 work plan.
In section F.3 Transit Operations: Estimated appropriations to support expenses, enter FY 2019 and the estimated annualized cost in FY 2020 using the 2.5% growth factor, if applicable. The spreadsheet will calculate 2021 and beyond by 2.5%. If your project is not expected to have recurring costs in FY 2021 and/or beyond, delete the calculation(s) in columns F-J.
In section F.4, enter the estimated appropriations to support contractual commitments and other expenses related to proposed capital.
In section F.5, enter any assumption(s) used to calculate the capital and operating dollars and revenues shown in sections F.1, F.2, F.3 and F.4.

## ProjReport Instructions
FY 2019 Durham-Orange Transit
Project Reporting Instructions
Project Reporting Forms (Operating Expansion and Capital Requests)
Agencies with Approved Durham-Orange Transit Projects are required to complete a Project Review Report at the end of each quarter. Each Approved project will have been submitted to the Durham-Orange Staff Working Group in a Microsoft Excel workbook, named with your Unique Project ID, a version and a date. After completing the Project Reporting form, rename the workbook so that it includes the relative quarter (i.e., Q1, Q2, Q3 or Q4) identifying it as the quarterly report.
Agencies are encouraged to coordinate reports internally and to have one point of contact for submitting reports in agency folders.
HINT: Reporting Agencies only need to complete sections highlighted GREEN.
How to Submit Requests
E-mail each Project workbook, one for each Unique Project ID #, which contains both a Project Request sheet and a Project Reporting sheet, to DOTransitProjects@gotriangle.org.
Instructions by Section
Project Progress
Complete all cells shaded GREEN.
In Quarter 1, enter in the progress of each Key Performance Indicator. In this section, keep the description brief. For example, input the percentage completed. Details will be included in the next section.
Project Status
Complete all cells shaded GREEN. Type in project status details under the appropriate quarter. Attach documents as needed noting it in row 39.
Financed Estimates
At the time of the report, enter in the year to date (YTD) Estimated Operating costs (cell D47) and/or the Estimated Capital Costs (cell D56) for the project. The charts will automatically fill. GoTriangle will prepare the official quarterly financial report.

## FY19 Exhibit A - Draft (hidden)
Unique Project ID# |  | Triangle Tax District |  |  |  |  | FY START DATE | 2018-07-01
18GOT_CD8 |  | Durham - Orange Transit Work Plan |  |  |  |  | FY 2019
Unique Request ID: [FY Project Start year] - [Three letter Agency] - [Project Number] |  | Project Review |  |  |  |  | 2018-06-30
FUND
Project Brief
Project Name |  | Requesting Agency |  | Project Contact |  |  | Estimated Operating Cost
Hillsborough Park-and-Ride |  | GoTriangle |  | Kevin Lewis |  |  | Base Year | 0
|  |  |  | klewis@gortiangle.org |  |  | Cumulative | 41525.1562
Estimated Start Date |  | Estimated Completion |  | Notes |  |  | Estimated Capital Cost
2017-07-01 |  | 2020-06-30 |  | (Add notes as appropriate) |  |  | Base Year | 80000 | FALSE
[7 empty] | Cumulative | 1270000 | FALSE
Project Description | [8 empty] | FALSE
A park and ride in Hillsborough will provide access to the GoTriangle Orange-Durham Express Route (ODX). The park and ride will have 35-50 parking spaces and a bus stop. The park and ride will be located along US 70 as defined by the Orange County 5-Year Bus Plan. | [10 empty] | TRUE
Alignment with Durham or Orange Transit Plan? |  |  | YES | [6 empty] | Operating | FALSE
[10 empty] | Capital Development | TRUE
Project Profile | [9 empty] | Capital Vehicle Acquisition | FALSE
Project Location? |  | Who will this Project serve? |  |  | What are the key benefits? |  |  |  |  | Both | FALSE
US70 Corridor |  | GoTriangle riders in Orange County |  |  | New park-and-ride facility |  |  |  |  | Operating - Administration | FALSE
Project Progress
Progress on Key Performance Indicators during project progress. These performance measures will be reported quarterly.
| Project Target Milestones |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
a) | CD-Project Development
b) | CD-Construction Start
c) | CD-Construction Completion
Project Status
Quarter 1 |  | Quarter 2 |  | Quarter 3 |  | Quarter 4
Documents Enclosed (if any) |  | Documents Enclosed (if any) |  | Documents Enclosed (if any) |  | Documents Enclosed (if any)
Financed Estimates - Funded by Durham and Orange Transit Plans
FY19 |  | EXPENDITURE
ESTIMATED OPERATING COSTS (YTD) |  | 858348 | -858348
TOTAL BUDGETED OPERATING COSTS |  | 0
% Utilized |  | 0%
FY19 |  | EXPENDITURE
ESTIMATED CAPITAL COSTS (YTD) |  |  | 1190000
TOTAL BUDGETED CAPITAL COSTS |  | 1190000
% Utilized |  | 0%
Durham
Orange
Durham & Orange
Note on B10: Praveen Sridharan: Replicated from Request Form
Note on D10: Praveen Sridharan: Replicated from Request form

## End-of-Year Reconciliations (hidden)
Triangle Tax District
Durham - Orange Transit Work Plan
Invoice Date:
|  | To: |  |  |  |  | Agency Name
|  | GoTriangle |  |  |  |  | Name
|  | Attn: Sharita Seibles |  |  |  |  | Address Line
|  | PO BOX 13787 |  |  |  |  | Address Line 2
|  | RTP, NC 27709 |  |  |  |  | City, ST ZIP Code
|  | sseibles@gotriangle.org |  |  |  |  | E-mail
|  | Phone: 919-485-7454 |  |  |  |  | Phone No.
|  | Fax: 919-485-7491 |  |  |  |  | Fax No.
PROJECT ID# | ITEM AND DESCRIPTION - BUS SERVICES |  | START DATE | END DATE | ACTUAL HRS | BUDGETED COST PER HR | ACTUAL COST PER HR | Difference | END-OF-YEAR RECONCILLIATION
0
0
0
0
0
| ITEM AND DESCRIPTION - INCREASED COST OF EXISTING SERVICES |  | START DATE | END DATE
| Inceased Cost of Existing Services - Route JU |  | 2014-01-01 | 2014-06-30 |  |  |  |  | 0
| Inceased Cost of Existing Services - Route HS |  | 2014-01-01 | 2014-06-30 |  |  |  |  | 0
0
0
0
[8 empty] | TOTAL | 0
PAYMENTS WILL NOT BE DISBURSED UNTIL THIS INVOICE IS REVIEWED BY TRIANGLE TAX DISTRICT

## Cap Expan Template (hidden)
Project Name |  | Requesting Agency |  | Project Contact |  |  | Estimated Capital Cost
0
Estimated Start Date |  | Estimated Completion |  | Estimated Annual Operating Costs
0
Project Summary
Project Justification / Business Case
Provide responses to each of the questions below
1. What is this project and where is is located ?
2. Who will this project serve and how will it improve service? What operating component in the Wake Transit Plan does it support?
3. How is this project related to the projected demand for future services?
4. How can outcomes be measured once this project is built/implemented?
5. What are the consequences if the project is delayed or denied?
6. Was this project contemplated in the Adopted Wake Transit Plan, and if so, how does this request relate to what was programmed in the Adopted Wake Transit Plan. If not, is this project in addition to projects included in the Wake Transit Plan or in lieu of projects included in the Adopted Plan?
Cost Break Down of Project Request
Cost Category | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Capital Costs
Design | [7 empty] | 0
Construction - Impelemtation | [7 empty] | 0
Equipment | 0 | [6 empty] | 0
Land - Right of Way | [7 empty] | 0
Other | [7 empty] | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Revenue
| FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Wake County Tax Revenue | 0 | [6 empty] | 0
Other Revenue
Federal | [7 empty] | 0
State | [7 empty] | 0
Other | [7 empty] | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL REVENUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Revenue Over (Under) Spending | 0
Operating Impact of Capital
Cost Category | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  | 0% |  |  | 0%
Operating Costs
Salary & Fringes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bus Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OPER. COSTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating Revenue
| FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  | 0% |  |  | 0%
Wake County Tax Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Revenue
Federal | [7 empty] | 0
State | [7 empty] | 0
Other | [7 empty] | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Revenue Over (Under) Spending | 0
Assumptions for Costs and Revenues Above:
Please state any assumptions used to calculate the capital and operating dollars and revenues shown above.
Note on H3: Ren Wiles: Linked to cell below.
Note on E4: Ren Wiles: Enter Contact E-mail
Note on E6: Ren Wiles: Add Notes.
Note on A8: Ren Wiles: Insert narrative description of project
Note on C64: Ren Wiles: Allows for growth rate from Year 2 to 4.
Note on F64: Ren Wiles: Allows for growth estimate, Year 5 to 7.

## Ops Req_Template (hidden)
Project Name |  | Requesting Agency |  | Project Contact |  |  | Estimated Annual Operating Costs
1049869
Summary
Justification / Business Case
Provide responses to each of the questions below
1. How does this case relate to the Wake Transit Plan?
2. Who will operate this expansion service and how will it improve services?
3. Is this a one-time request?
4. How is this expansion related to the projected demand for future service?
5. What are the expected outcomes if this request is funded? What is the alternative if the request is not funded?
6. If applicable, describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function
7. What is the timeframe for the request? Are you requesting a full year of funds or a partial year to be annualized in future fiscal years?
8. For bus operating projects, please provide:
a) Target Start Date
b) Span
c) Frequency
d) Assets Used
e) Geographic Termini
f) Major Destinations Served
9. Besides dollars requested from the Wake Transit Work Plan, are any local dollars being applied to this operating request? Are there any new federal or state funds contemplated as a funding source?
Cost Breakdown of Request
Cost Category | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  | 2.5% |  |  | 2.5%
Operating Costs
Salary & Fringes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
Bus Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OPER. COSTS | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
Operating Revenue
| FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  | 2.5% |  |  | 2.5%
Wake County Tax Revenue | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
Other Revenue
Federal | [7 empty] | 0
State | [7 empty] | 0
Other | [7 empty] | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
[7 empty] | Revenue Over (Under) Spending | 0
Assumptions for Operating Costs and Revenues Above:
Please state any assumptions used to calculate the operating dollars and revenues shown above. What is loaded into the proposed expenditures?
Costs for the on-board surveys are estimated based on similar recent surveying efforts for GoTriangle and GoDurham, aggregated for all of the transit systems in Wake County. The community survey is a best estimate based on similar efforts in Charlotte and previous surveys conducted by the Regional Transportation Alliance to gauge attitudes of Wake County voters towards a potential
Note on E4: Ren Wiles: Enter Contact E-mail
Note on A6: Ren Wiles: Insert narrative description of project
Note on C58: Ren Wiles: Allows for growth rate from Year 2 to 4.
Note on F58: Ren Wiles: Allows for growth estimate, Year 5 to 7.

## Ops Req_Customer-Community Surv (hidden)
Project Name |  | Requesting Agency |  | Project Contact |  |  | Estimated Annual Operating Costs
Customer and Community Survey |  | Go Triangle |  | Erik Landfried |  |  | 1049869
elandfried@gotriangle.org
Summary
In FY 2018 and each successive year, GoTriangle and the other transit agencies in Wake County will engage consultants for two surveys: a county-wide customer satisfaction survey that collects basic statistics about transit riders and their opinions of the system, and a community survey that tracks perceptions of transit for the whole county – whether those surveyed ride transit or not. In FY 2019, and every three years thereafter (FY 2022, FY 2025…), the customer satisfaction survey will be expanded to collect route-level statistics for each route in Wake County.
Justification / Business Case
Provide responses to each of the questions below
1. How does this case relate to the Wake Transit Plan?
Both customer satisfaction and community surveys were conducted when the Adopted Wake County Transit Plan was being developed, to identify specific transit needs and set the policies that guide transit investment. Continued community engagement will keep the plan up to date and ensure that the implementation of the plan is meeting the needs of all Wake County residents.
2. Who will operate this expansion service and how will it improve services?
GoTriangle will manage the survey consultants, coordinating with the other transit agencies as needed. GoTriangle already has extensive experience managing customer satisfaction surveys for both the GoTriangle and GoDurham systems.
3. Is this a one-time request?
No, surveys will continue on an annual cycle.
4. How is this expansion related to the projected demand for future service?
Regularly surveying customers about their travel patterns and the transit system’s needs will ensure that transit system leadership has an up-to-date view of where more service is needed and where the system needs to focus its attention. Surveying external customers will also help transit system leadership identify services that could attract non-riders to transit
5. What are the expected outcomes if this request is funded? What is the alternative if the request is not funded?
If the request is funded, the transit partners will have detailed, regularly-updated data about the system’s rider base and about perceived needs for the system. If the request is not funded, statistical data will be limited to ad hoc surveys performed by transit staff – there will not be any data about non-riders, and planners will have to wait longer for updated information about riders’ needs. These surveys may also be different from one transit agency to the next, making it difficult to compare across agencies and compile a complete picture of transit service in Wake County.
6. If applicable, describe proposed responsibilities and duties for new position requests. Provide each major intended function, and the percentage of time devoted to each function
Not Applicable.
7. What is the timeframe for the request? Are you requesting a full year of funds or a partial year to be annualized in future fiscal years?
The surveys will most likely be conducted in the fall of each year (beginning in fall 2017). The amount will not need to be annualized for future years, but every third year (starting in fall 2018/FY 2019) will have a higher amount since the route-level survey will be conducted, which is a more labor- and data-intensive process.
8. For bus operating projects, please provide:
a) Target Start Date
b) Span
c) Frequency
d) Assets Used
e) Geographic Termini
f) Major Destinations Served
Not Applicable
9. Besides dollars requested from the Wake Transit Work Plan, are any local dollars being applied to this operating request? Are there any new federal or state funds contemplated as a funding source?
No, the cost of the surveys would be fully covered by Wake Transit Plan funds
Cost Breakdown of Request
Cost Category | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  | 2.5% |  |  | 2.5%
Operating Costs
Salary & Fringes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
Bus Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OPER. COSTS | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
Operating Revenue
| FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Total
Growth Factors |  | 2.5% |  |  | 2.5%
Wake County Tax Revenue | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
Other Revenue
Federal | [7 empty] | 0
State | [7 empty] | 0
Other | [7 empty] | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 125000 | 179375 | 131328 | 134611 | 193167 | 141426 | 144962 | 1049869
[7 empty] | Revenue Over (Under) Spending | 0
Assumptions for Operating Costs and Revenues Above:
Please state any assumptions used to calculate the operating dollars and revenues shown above. What is loaded into the proposed expenditures?
Costs for the on-board surveys are estimated based on similar recent surveying efforts for GoTriangle and GoDurham, aggregated for all of the transit systems in Wake County. The community survey is a best estimate based on similar efforts in Charlotte and previous surveys conducted by the Regional Transportation Alliance to gauge attitudes of Wake County voters towards a potential
Note on E4: Ren Wiles: Enter Contact E-mail
Note on A6: Ren Wiles: Insert narrative description of project
Note on C58: Ren Wiles: Allows for growth rate from Year 2 to 4.
Note on F58: Ren Wiles: Allows for growth estimate, Year 5 to 7.