## Slide 1
Engineering
Major Projects: Raleigh Office
Minor Projects: Division Office
Notes: -This is a NCDOT policy, not a FHWA policy; it’s meant to avoid conflicts of interest that may arise when the same firm is involved with both phases.
-An exception request may be made to our office, at the stage of final plans. The request should include how the LGA will provide oversight to eliminate conflicts of interest; also consider scale of the project, impact, risks, and quantity of work.
-Letter should be submitted to our office; a set of final plans can be submitted directly to the Construction Office.
-The LGA can begin their solicitation for CEI (should not occur until after construction funds are authorized); if exception is allowed, then a proposal from the design firm can be accepted.
-The only time the consultant could be extended the contract without a new solicitation is if the original contract included CEI (although we are now trying to be vigilant up front about not including this phase of work) and the consultant was originally acquired under a qualifications-based selection process.

## Slide 2: Project Design
What’s “minor”? Simple design, no complicating issues.
What’s major? – Closed Drainage systems, culverts, other structures – things a design unit in Raleigh must review.
All projects should use the NCDOT 2012 Standard Specs and Standard Drawings.

## Slide 3: Project Review Time
MINOR
Email or Paper Submittal
Short Review Time – usually within 2 weeks
But…..there are dozens of projects (not just LAPP projects), and typically 1 reviewer!
MAJOR
Paper copies and electronic plans sent to Roadway Design.
Several weeks due to multiple reviewing units and internal coordination.
Is it a complete set of plans and specifications?
September is the big “due” month, so everything takes longer due to shear volume.

## Slide 4: Major Projects
Scoping Meeting – Recommended with NCDOT, Municipality & Consultant prior to execution of Consultant Contract
25%, 75% (R/W), 90% & 100% Plan Reviews
U & R designated STIP projects to be submitted to NCDOT Plan Checking at 100% final review
Final Contract Documents to be reviewed by NCDOT Proposals & Contracts
Municipal Project Design & Review Criteria
https://connect.ncdot.gov/projects/Roadway/RoadwayDesignAdministrativeDocuments/Municipal- Developer%20Submittals%20Guideline.pdf
Planning Document (PCE, CE, EA, etc.) progresses concurrently with design plans
  Corridor Modeling – Recommended, but not required

## Slide 5: Major Projects
NCDOT Point of Contact
FHWA delegates authority to NCDOT to review and approve project designs on and off its maintained system
Who will maintain? NCDOT or Municipality
Project to be built with long term maintenance and expandability in mind
  Project not to require immediate repairs or action by NCDOT or Municipality
  Potential Project Problems
  Communication & Collaboration – A successful project is the result of the Municipality, Consultant , NCDOT & FHWA working together

## Slide 6: Contract Proposal
Contract Proposal
  Use Line-Up Sheet – see LPMO Handbook for more information
  Check effective dates for Specs when updating proposals.
  Do NOT use AIA, EJCDC or SCO Specs – often causes conflict.
  Division or Contract Standards will approve
  Need Line Item Estimate at this point for goal setting

## Slide 7: Specialty or Proprietary Items
Avoid if at all possible.
If using name brand items, must list 3 brands and also “or equivalent”.
Specialty Items MUST be approved well in advance of letting. i.e. trash cans on a streetscape project where matching existing trashcans on previous projects is desired. Approval could take several weeks!

## Slide 8: Project Engineers
Major Projects:
Mohammad Mahjoub
Minor Projects:
    Division 4 Jerry Page, PE
    Division 5 Mike Kneis, PE
    Division 6 Jerry Bradley, PE